## Sheet1
ID | Milestone | Epic | Task | Start Date | End Date | Duration (days) | Status | Parent Task | Comments
5 | 1. System Foundation | System Setup | Design Login Form (via Form Designer) | 2025-09-22 | 2025-09-22 | 1 | Not Started | System Setup | GUI login form
7 | 1. System Foundation | System Setup | Design Global Menu (via Form Designer) | 2025-09-24 | 2025-09-24 | 1 | Not Started | System Setup | Welcome screen
1 | 1. System Foundation | System Setup | Setup PostgreSQL DB (xactapp_db) | 2025-09-17 | 2025-09-17 | 1 | Completed | System Setup | Create database, users, permissions
2 | 1. System Foundation | System Setup | Load schema & seeders (roles, perms, company) | 2025-09-18 | 2025-09-18 | 1 | Started | System Setup | Run SQL schema & seed scripts
3 | 1. System Foundation | System Setup | Build RBAC helper program (rbac.4gl) | 2025-09-19 | 2025-09-19 | 1 | Not Started | System Setup | Provides can() function for permissions
4 | 1. System Foundation | System Setup | Build Login program (main.4gl) | 2025-09-20 | 2025-09-21 | 2 | Not Started | System Setup | Console version first
6 | 1. System Foundation | System Setup | Build Global Menu program (menu.4gl) | 2025-09-22 | 2025-09-23 | 2 | Not Started | System Setup | Navigation + toolbar
9 |  | Debtors Module | Design Debtors Master (Form Designer) | 2025-09-26 | 2025-09-26 | 1 | Not Started | Debtors Module | Customer details UI
11 |  | Debtors Module | Design Debtors Transactions (Form Designer) | 2025-09-28 | 2025-09-28 | 1 | Not Started | Debtors Module | Transaction enquiry
15 |  | Creditors Module | Design Creditors Master (Form Designer) | 2025-10-02 | 2025-10-02 | 1 | Not Started | Creditors Module | Supplier details UI
17 |  | Creditors Module | Design Creditors Transactions (Form Designer) | 2025-10-04 | 2025-10-04 | 1 | Not Started | Creditors Module | Transaction enquiry
21 |  | Stock & Warehouse | Design Stock Master (Form Designer) | 2025-10-08 | 2025-10-08 | 1 | Not Started | Stock & Warehouse | Stock UI
23 |  | Stock & Warehouse | Design Stock Transactions (Form Designer) | 2025-10-10 | 2025-10-10 | 1 | Not Started | Stock & Warehouse | Stock movements enquiry
25 |  | Stock & Warehouse | Design Warehouse Master (Form Designer) | 2025-10-12 | 2025-10-12 | 1 | Not Started | Stock & Warehouse | Safety tags, categories
27 |  | Stock & Warehouse | Design Bin Master (Form Designer) | 2025-10-14 | 2025-10-14 | 1 | Not Started | Stock & Warehouse | Bin UI
30 |  | Sales Module | Design Sales Quote (Form Designer) | 2025-10-18 | 2025-10-18 | 1 | Not Started | Sales Module | Quote entry
32 |  | Sales Module | Design Sales Order (Form Designer) | 2025-10-20 | 2025-10-20 | 1 | Not Started | Sales Module | Order entry
34 |  | Sales Module | Design Sales Invoice (Form Designer) | 2025-10-23 | 2025-10-23 | 1 | Not Started | Sales Module | Invoice entry
36 |  | Sales Module | Design Sales Credit Note (Form Designer) | 2025-10-25 | 2025-10-25 | 1 | Not Started | Sales Module | CN entry
39 |  | Purchases Module | Design Purchase Order (Form Designer) | 2025-10-29 | 2025-10-29 | 1 | Not Started | Purchases Module | PO entry
41 |  | Purchases Module | Design Purchase Invoice (Form Designer) | 2025-10-31 | 2025-10-31 | 1 | Not Started | Purchases Module | PINV entry
45 |  | Finance & Payments | Design Journals (Form Designer) | 2025-11-05 | 2025-11-05 | 1 | Not Started | Finance & Payments | Simple posting screen
47 |  | Finance & Payments | Design Payments (Form Designer) | 2025-11-07 | 2025-11-07 | 1 | Not Started | Finance & Payments | Payment entry
8 |  | Debtors Module | Build Debtors Master program (dl_mast.4gl) | 2025-09-24 | 2025-09-25 | 2 | Not Started | Debtors Module | CRUD for dl01_mast
10 |  | Debtors Module | Build Debtors Transactions program (dl_trans.4gl) | 2025-09-26 | 2025-09-27 | 2 | Not Started | Debtors Module | Manage dl30_trans
12 |  | Debtors Module | Add Debtors History logging (dl40_hist) | 2025-09-28 | 2025-09-28 | 1 | Not Started | Debtors Module | Record all changes
13 |  | Debtors Module | Test Debtors end-to-end | 2025-09-29 | 2025-09-29 | 1 | Not Started | Debtors Module | Verify CRUD + posting
14 |  | Creditors Module | Build Creditors Master program (cl_mast.4gl) | 2025-09-30 | 2025-10-01 | 2 | Not Started | Creditors Module | CRUD for cl01_mast
16 |  | Creditors Module | Build Creditors Transactions program (cl_trans.4gl) | 2025-10-02 | 2025-10-03 | 2 | Not Started | Creditors Module | Manage cl30_trans
18 |  | Creditors Module | Add Creditors History logging (cl40_hist) | 2025-10-04 | 2025-10-04 | 1 | Not Started | Creditors Module | Record all changes
19 |  | Creditors Module | Test Creditors end-to-end | 2025-10-05 | 2025-10-05 | 1 | Not Started | Creditors Module | Verify CRUD + posting
20 |  | Stock & Warehouse | Build Stock Master program (st_mast.4gl) | 2025-10-06 | 2025-10-07 | 2 | Not Started | Stock & Warehouse | CRUD for st01_mast, st_cat
22 |  | Stock & Warehouse | Build Stock Transactions program (st_trans.4gl) | 2025-10-08 | 2025-10-09 | 2 | Not Started | Stock & Warehouse | Manage st30_trans
24 |  | Stock & Warehouse | Build Warehouse Master program (wh_mast.4gl) | 2025-10-10 | 2025-10-11 | 2 | Not Started | Stock & Warehouse | CRUD for wh01_mast
26 |  | Stock & Warehouse | Build Bin Master program (wb_mast.4gl) | 2025-10-12 | 2025-10-13 | 2 | Not Started | Stock & Warehouse | CRUD for wb01_mast
28 |  | Stock & Warehouse | Test Stock & Warehouse | 2025-10-14 | 2025-10-15 | 2 | Not Started | Stock & Warehouse | Verify IN/OUT posting
29 |  | Sales Module | Build Sales Quote program (sa30.4gl) | 2025-10-16 | 2025-10-17 | 2 | Not Started | Sales Module | CRUD + posting
31 |  | Sales Module | Build Sales Order program (sa31.4gl) | 2025-10-18 | 2025-10-19 | 2 | Not Started | Sales Module | CRUD + posting
33 |  | Sales Module | Build Sales Invoice program (sa32.4gl) | 2025-10-20 | 2025-10-22 | 3 | Not Started | Sales Module | Updates Debtors + Stock
35 |  | Sales Module | Build Sales Credit Note program (sa33.4gl) | 2025-10-23 | 2025-10-24 | 2 | Not Started | Sales Module | Reversals
37 |  | Sales Module | Test Sales end-to-end | 2025-10-25 | 2025-10-26 | 2 | Not Started | Sales Module | Verify stock/dl posting
38 |  | Purchases Module | Build Purchase Order program (pu30.4gl) | 2025-10-27 | 2025-10-28 | 2 | Not Started | Purchases Module | CRUD + posting
40 |  | Purchases Module | Build Purchase Invoice program (pu31.4gl) | 2025-10-29 | 2025-10-30 | 2 | Not Started | Purchases Module | Updates Creditors + Stock
42 |  | Purchases Module | Test Purchases end-to-end | 2025-10-31 | 2025-11-01 | 2 | Not Started | Purchases Module | Verify stock/cl posting
43 |  | Finance & Payments | Seed Chart of Accounts (gl01_acc) | 2025-11-02 | 2025-11-02 | 1 | Not Started | Finance & Payments | Core GL setup
44 |  | Finance & Payments | Build Journals program (gl_jrn.4gl) | 2025-11-03 | 2025-11-04 | 2 | Not Started | Finance & Payments | CRUD for gl30, gl31
46 |  | Finance & Payments | Build Payments program (payt30.4gl) | 2025-11-05 | 2025-11-06 | 2 | Not Started | Finance & Payments | DR receipts & CR payments
48 |  | Finance & Payments | Link Payments to DL/CL/GL posting | 2025-11-07 | 2025-11-08 | 2 | Not Started | Finance & Payments | Ensure journals updated
49 |  | Finance & Payments | Test Finance & Payments | 2025-11-09 | 2025-11-10 | 2 | Not Started | Finance & Payments | Verify postings
50 |  | Final | Run UAT with sample data | 2025-11-11 | 2025-11-12 | 2 | Not Started | Final | Test all modules
51 |  | Final | Fix bugs & polish UI | 2025-11-13 | 2025-11-15 | 3 | Not Started | Final | Ensure stability
52 |  | Final | Prepare demo presentation | 2025-11-16 | 2025-11-16 | 1 | Not Started | Final | Delivery